## Gantt_Data
SYSTEM GANTT CHART
SUMMARY:
Task ID | Task | Start Date | End Date | Duration (days) | Responsible | Name | Status
1 | Project Planning | 2025-08-13 | 2025-08-20 | 8 | Leader | All group | Not Started
2 | Requirements Gathering | 2025-08-27 | 2025-09-03 | 8 | Analyst | Perez,Vander | Not Started
3 | Design | 2025-09-10 | 2025-09-17 | 8 | Designer | Tomes/Villanueva | Not Started
4 | Development | 2025-09-24 | 2025-10-01 | 8 | Developer | Solayao Emanuel | Not Started
5 | Testing | 2025-10-08 | 2025-10-15 | 8 | Team Lead | All group | Not Started
6 | Deployment | 2025-10-22 | 2025-10-29 | 8 | Developer | Solayao Emanuel | Not Started

## Instructions
Instructions
Gantt Chart Template Instructions
---------------------------------
This workbook includes a 'Gantt_Data' sheet with sample tasks. Columns included:
- Task ID
- Task
- Start Date
- End Date
- Duration (days)
- Dependencies
- Responsible
- Status
How to create a simple Gantt chart in Excel:
1. Select the Gantt_Data table (Task, Start Date, Duration).
2. Insert -> Bar Chart -> Stacked Bar.
3. In the chart, set the first series (Start Date) to have no fill (so bars start at Start Date).
- Format Data Series -> Fill -> No fill.
4. The second series (Duration) will display the task durations as bars.
5. Reverse the vertical axis so tasks appear top-to-bottom in the original order:
- Format Axis -> Categories in reverse order.
6. Optionally add gridlines, change date axis formatting, and color-code bars by Status or Responsible.
7. For Google Sheets:
- Use a stacked bar chart similarly, or use conditional formatting across a calendar grid for a simple visual Gantt.
Suggested columns to edit for your project:
- Replace sample tasks with your project tasks.
- Set actual Start and End Dates.
- Update Duration (or set Duration formula: End Date - Start Date + 1).
- Fill Dependencies if tasks depend on previous tasks (Task IDs).
- Update Responsible and Status columns for tracking.
Tip: For a calendar-style Gantt (in Excel/Sheets), create columns for each date and use formulas or conditional formatting to mark active task days.

## GANTT CHART
DAYS
TASK ID | TASK | STATUS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Project Planning | Plan
Actual
2 | Requirements Gathering | Plan
Actual
3 | Design | Plan
| 3.1 Data Flow Diagram | Actual
3.2 Detailed Data Flow Diagram
4 | Development | Plan
Actual
5 | Testing | Plan
Actual
6 | Deployment | Plan
Actual
7 | Documentation & Handover | Plan